## Features
Sıra No | Developer | Tester | Feature / Drop | Epic | Testing level |  |  | Main Tools | Framework | Tools
1 |  |  | Home page | WebElements must be Visible and Usable on Home Page | UI testing | Backend Testing will be on next Sprint | Database Testing will be on next Sprint | Java + Selenium | TestNG DDT | Jira-Xray /Git GitHub
2 |  |  | Login Page | Must be able to login using the Login/Login page. | UI testing | Backend Testing will be on next Sprint | Database Testing will be on next Sprint | Java + Selenium | TestNG DDT | Jira-Xray /Git GitHub
3 |  |  | Registration Page | It should be able to register using the Registration page. | UI testing | Backend Testing will be on next Sprint | Database Testing will be on next Sprint | Java + Selenium | TestNG DDT | Jira-Xray /Git GitHub
4 |  |  | Hotel List | Hotel should be added as an administrator | UI testing | Backend Testing will be on next Sprint | Database Testing will be on next Sprint | Java + Selenium | TestNG DDT | Jira-Xray /Git GitHub
5 |  |  | Hotel List | As an Administrator, the Hotel should be able to be updated | UI testing | Backend Testing will be on next Sprint | Database Testing will be on next Sprint | Java + Selenium | TestNG DDT | Jira-Xray /Git GitHub
6 |  |  | Hotel Rooms | Room should be added as Admin | UI testing | Backend Testing will be on next Sprint | Database Testing will be on next Sprint | Java + Selenium | TestNG DDT | Jira-Xray /Git GitHub
7 |  |  | Hotel Rooms | As an Administrator, Room should be able to be updated | UI testing | Backend Testing will be on next Sprint | Database Testing will be on next Sprint | Java + Selenium | TestNG DDT | Jira-Xray /Git GitHub
8 |  |  | Room reservations | Room reservation can be added as an administrator | UI testing | Backend Testing will be on next Sprint | Database Testing will be on next Sprint | Java + Selenium | TestNG DDT | Jira-Xray /Git GitHub
9 |  |  | Room reservations | Room reservation should be able to be updated as Admin | UI testing | Backend Testing will be on next Sprint | Database Testing will be on next Sprint | Java + Selenium | TestNG DDT | Jira-Xray /Git GitHub
10 |  |  | Room reservations | Room reservation can be added as a user | UI testing | Backend Testing will be on next Sprint | Database Testing will be on next Sprint | Java + Selenium | TestNG DDT | Jira-Xray /Git GitHub
|  |  | Note : | Her USerStory icin minium 5 TestCase yazilmasini istiyoruz…

## Project Tracking
| Project Tracking | Durum
1 | Issuing EPICs | NOT YET
2 | Creation of USs. | DONE
3 | Holding a grooming meeting (PO tells User Stories and a general scoring is done.)
4 | Sprint Planning (USs are scored and task distribution is made.)
5 | Holding daily meetings
6 | Creating testcases with excel file
7 | Creating a Jirada Team/Creating a Project
8 | Export to Jira
9 | Creating public repository on Github and adding other team members
10 | Creating framework, submitting to Github
11 | Writing test codes
12 | Execution of codes.
13 | Making necessary updates in Jira. (Ticket or necessary corrections)
14 | When the bug is found, this issue will be created and assigned to the relevant developer and sent to TODO.
15 | After the BUGs found are fixed, those tests will be run again and it will be ensured that they are problem-free.
16 | Demo Meeting will be held (Sprint Review Meeting)
17 | Retro Meeting will be held.
|  |  | US_0001 | US_0002 | US_0003 | US_0004 | US_0005 | US_0006 | US_0007 | US_0008 | US_0009 | US_0010
Creating one Test Case for each Acceptance Criteria in Excel (Total 5 Test Cases)
Creating one Test Case for each Acceptance Criteria in Jira (Total of 5 Test Cases)
Creating the Test Steps of each Test Case created in Jira in the Test Case
Creating one Pre-Condition for each User Story in Jira
Creating one Test Set for each User Story in Jira
Creating one Test Plan for each User Story in Jira
Creating one Test Execution for each Test Case within the created Test Plan
Creating and running Test Cases for Acceptance Criteria in Intellij IDE
Manual execution of Test Executions created in Jira.

## Product Backlog
User_Story_ID | Description | Acceptance Criteria | Priority | Validation | Point
US_0001 | "As a user, To get detailed information about the hotel, To see the articles on the home page and I want to be able to use redirects."
US_0002 | "As a Manager, In order to use the opportunities offered to the manager, using pre-registered username and password I want to be able to login to the site"
US_0003 | As a User, In order to use the opportunities offered to users. I want to register to the system using valid data.
US_0004 | "As a Manager, To keep hotel information up to date, I want to add hotel successfully with valid information."
US_0005 | As a Manager, To keep hotel information up to date, I want to be able to update or delete hotel information.
US_0006 | """As an Administrator, To keep room information up-to-date and I want to be able to add a hotel room.""
US_0007 | "As a Manager, In order to keep the room information up to date, I want to be able to update or delete room information."
US_0008 | "As a Manager, In order to keep the reservation information up to date, I want to be able to create reservation information."
US_0009 | "As a Manager, In order to keep the reservation information up to date, I want to be able to update or delete reservation information."
US_0010 | "As a User, To stay at the hotel I want to be able to make a room reservation."

## US0001
User Story ID | Test Case ID | Test Objective | Pre-Condition | Steps | Test Data | Expected Result | Actual Result | Status